## Status Report
RBFCU NBO(NetBranch Online) Spring MVC Migration Old Technology - Struts 1.x
Phase 1
S.No | Activity | Number of Days | Start Date | End Date | Development Status
One Time Activity/ Configuration For migration
1 | configure org.springframework.web.servlet.DispatcherServlet in web.xml file | 5 days | 2017-10-02 | 2017-10-06 | Completed
2 | Include below bean entries in servlet-context xml file ResourceBundleMessageSource TilesViewResolver TilesConfigurer | 2 days | 2017-10-09 | 2017-10-10 | Completed
3 | Maintaining new set of tiles-*.xml to use apache tiles-3 specification | 5 days | 2017-10-11 | 2017-10-17 | Completed
4 | Find solution for changing Struts tag libraries to Spring Tag libraries | 3 days | 2017-10-18 | 2017-10-20 | Completed
5 | Configure view context xml for forwarding and redirecting urls without configuring controllers. | days | 2017-10-23 | 2017-10-24 | Completed
Recurring activities for every module migration
6 | Findout Procedure for converting action classes into controllers. | 5 days | 2017-10-25 | 2017-10-31 | Completed
7 | Findout approach for converting formBean to spring form. | 3 days | 2017-11-01 | 2017-11-03 | Completed
8 | Findout approach to Converting JSPs with Struts tag libraries to spring tag libraries | 3 days | 2017-11-06 | 2017-11-08 | Completed
9 | Replace global header jsp with "preHeader.jspf" and | 2 days | 2017-11-09 | 2017-11-13 | Completed
10 | Remove tiles configuration from jsp. tiles configuration needs to be moved to tiles definition xml. | 5 days | 2017-11-14 | 2017-11-20 | Completed
11 | Create Generic Display Error message which is specific to Spring Error framework level and demo for whar are the steps needs to follow for migrating struts to spring | 4 days | 2017-11-21 | 2017-11-24 | Completed
S.No | Module Name | Activities | Number of Days | Start Date | End Date | Development Status
1 | Certificates & IRA Plans | 1. Converted exisitng functionality which is used for view all the certificates and IRA plans for the particular user. 2. View is similar to exisitng system but server side framework and code will change. 3. Converted all action, actionforms, jsps and tiles file into spring framework related controllers, forms, jsps, tiles 3.0 4.What are tasks mentioned in the Recurring tasks on the above table, all should be implemented fot this module. 5.Changes required for Mobile app and full site. 6.Fixed Bugs from UAT and sent for demo. | 5 days | 2017-11-27 | 2017-12-01 | Completed
Summary
Activity
2 | Investments | 1. This modules is communicated with third party CBSI website so here implemented session attributes which is related to spring frame work. 2. Created controllers and which is communicated to thirdparty website and view the invetment page. 3. User can browse and do operation in the RB Financial screen. 4.Repeated the all activites on the Recurring block. 5.Changes required for Mobile app and full site. 6.Fixed Bugs from UAT and sent for demo. | 5 days | 2017-12-04 | 2017-12-08 | Completed
Investments
RB Financial
3 | My Messages | 1. This modules is communicated with third party CBSI website so here implemented session attributes which is related to spring frame work. 2. Created controllers and which is communicated to thirdparty website and view the invetment page. 3. User can browse and do operation in the RB Financial screen. 4.Repeated the all activites on the Recurring block. 5.Changes required for Mobile app and full site. 6.Fixed Bugs from UAT and sent for demo. | 7 days | 2017-12-11 | 2017-12-19 | Completed
Messages
Inbox
Send
Phase 2
4 | My Profile | 1.Based on existing functionality, convert the action classes into Spring controllers. 2.Remove all struts tag libraries dependencies from JSP's which are related to MyProfile Module. 3.Spring validation using validator classes. 4.Use Tiles definition for refering jsp pages. 5.Changes required for Mobile app and full site. 6.Fixed Bugs from UAT and sent for demo. | 8 days | 2017-12-20 | 2017-12-29 | Completed
Update Username
Update SQA
5 | Authentication | 1.Analyze for spring security feasible to NBO or not, if yes then provide the solution for developing spring security to the NBO project. 2. Implemented new upgrade spring security for the authentication to NBO/RBFCU website. 3.Created new config files related to spring security. 4. Enabled Cross site Request Forgery (CSRF) for all URls in the RBFCU website for preventing from hiking and other cyber crime attacks. 5. As part of this designed and implemented some URls protection, giving read-only access based on the roles. 6. Prepared documentation for spring security and present demo to other team members. 7.Fixed Bugs from UAT | 25 days | 2018-01-01 | 2018-02-02 | Completed
First time login
Forgot Username
Forgot SQA
CSRF Integration
Safe Url Implementation, Spring security Implementation
6 | Transfers & Payments | 1.Findout the what are the dependency modules link with coversion of transfers. 2.Convert to all places where transfers module is referenced. 3. Implemented spring related changes to existing transfers module, which are mentioned above as recurring activities. 4. Fix bugs from UAT. 5.Give demo to Business people and team. |  | 2018-02-05 |  | Pending
Make/Schedule Transfer
Manage Schedule Transfers
Phase 3
| Favorites List - Add to Favorites List | 1.Findout the what are the dependency modules link with coversion of transfers favorites. 2.Convert to all places where transfers module is referenced. 3. Change the already existing design , which is related to spring framework level. 4. Implemented spring related changes to existing transfers module, which are mentioned above as recurring activities. 5. Fix bugs from UAT. 6.Give demo to Business people and team. |  | 2018-02-19 |  | Pending
Favorites List - Manage Favorites List
Line of Credit Advance
Master Card Advance
MasterCard Balance Transfer
7 | Accounts:Home | 1.Findout the what are the dependency modules link with coversion of Accounts page. 2.Convert to all places where accounts module is referenced. 3. Change the already existing design , which is related to spring framework level. 4. Implemented spring related changes to existing accounts module, which are mentioned above as recurring activities. 5. Fix bugs from UAT. 6.Give demo to Business people and team. |  | 2018-03-05 |  | Pending
Open Account
Open Certificate
Order Checks
| eAlerts |  |  |  |  | Not Yet Started
eDocuments
Manage Cards
Statements
Rates
Tax Information
Loans - Apply ¦ Status
Manage Guest Users
Manage Account Grouping
My Offers
Phase 4
8 | ePay |  |  |  |  | Not Yet Started
Log on to ePay
Enroll in epay
Overview and Pricing
FAQ
epay Demo
Terms and Conditions
9 | Loans
Activity
Line Of Credit Advance
Apply
Rates
Phase 5
10 | Master Card |  |  |  |  | Not Yet Started
Summary
Payment
Cash Advance
Balance Transfer
Platinum MasterCard
Start Points Redemption
MasterCard
Secure Code Credit Cards
Apply
Application Status
Paperless Statements
Travel Notification
Messages
Check Re-order