## Sheet1
Website Re-Design
S.No | Activity | Tasks | Number of Days | Start Date | End Date | Resource/Team | Development Status | Project Status
1 | Home Page | Involved in business meetings and gathered requirements with Business | 5days | 2017-08-01 | 2017-08-07 | Natalie Tate | Completed | Completed
Started Creating Template for Home Pages
Developed Component's for Home pages
Developed Accessibility Features
Fixed defects for the Home pages and sent for demo
2 | Banking Modules | Gathered requirements from Business | 4days | 2017-08-08 | 2017-08-11 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Banking Pages
Developed Component's for Banking pages
Developed Accessibility Features
Fixed defects for the Banking pages and sent for demo
3 | Loans | Gathered requirements from Business | 3days | 2017-08-14 | 2017-08-16 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Loans Pages
Developed Component's for Loans pages
Developed Accessibility Features
Fixed defects for the pages and sent for demo
4 | Home Loans & reality | Gathered requirements from Business | 5days | 2017-08-17 | 2017-08-23 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home loans and reality Pages
Developed Component's for Home loans and reality Pages
Developed Accessibility Features
Fixed defects for the Home loans and reality Pages and sent for demo
5 | Business | Gathered requirements from Business | 4days | 2017-08-24 | 2017-08-29 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Business Pages
Developed Component's for Business pages
Developed Accessibility Features
Fixed defects for the Business page and sent for demo
6 | Educational Resources | Gathered requirements from Business | 5days | 2017-08-30 | 2017-09-06 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Educational Resources Pages
Developed Component's for Educational Resources page
Developed Accessibility Features
Fixed defects for the Educational Resources page and sent for demo
7 | Investments | Gathered requirements from Business | 5days | 2017-09-07 | 2017-09-13 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Investments Page
Developed Component's for Investments page
Developed Accessibility Features
Fixed defects for the Home page and sent for demo
8 | Insurance | Gathered requirements from Business | 4days | 2017-09-14 | 2017-09-19 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Insurance Page
Developed Component's for Insurance page
Developed Accessibility Features
Fixed defects for the Home page and sent for demo
9 | Educational Resources | Gathered requirements from Business | 3days | 2017-09-20 | 2017-09-22 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home Page
Developed Component's for Home page
Developed Accessibility Features
Fixed defects for the Home page and sent for demo
10 | Investments | Gathered requirements from Business | 5days | 2017-09-25 | 2017-09-29 | Natalie Tate | Completed
Collected Designs from visual designers
Started Creating Template for Home Page
Developed Component's for Home page
Developed Accessibility Features
Fixed defects for the Home page and sent for demo
Loan Status Re-Design
11 | Loans Status Menu page | Continued working Development on Loan status Re design Project | 5days | 2017-10-02 | 2017-10-06 | Paul Ripley | Completed | In Progress
Removed old CSS styling
Created new Template structure according to the new visual design
Developed the loan Menu page
Deployed Loan menu page for UAT
Fixed Bugs from UAT and sent for demo
12 | Loan status page | Started working on Loan status page | 4days | 2017-10-10 | 2017-10-13 | Paul Ripley | Completed
Developed loan status page Action Items according to the design
Re-Organized the Properties of application
Added new data properties from Data base which are introduced in redesign
Deployed Loan Status page for UAT
Fixed Bugs from UAT and sent for demo
13 | Accepting and decaling pages | Developed pages for accepting loan criteria | 2days | 2017-10-16 | pending | Paul Ripley | Pending
Developed pages for declining loan Criteria
Deployed in UAT environment for testing
Fixed Bugs from UAT and sent for demo
14 | Document Upload items | Started working On Document Upload Items | 2days | 2017-10-18 | pending | Paul Ripley | Pending
Developed Functionality for Uploading Documents
Developed Functionality for multiple Uploading Documents at one time
Adding a new Feature to remove and add a document Dynamically